## Sheet1
Author | Malcolm Knapp
Date | 2017-03-10
Project | LPE Inverter
Reviewer | Document | Version | Issue | Suggestion | Documentation Updated
Malcolm Knapp | Review List | ? | No Version on Review List | Add a version
Malcolm Knapp | Review List | ? | It is unclear what Spec refers too | Clarify what you mean by this
Malcolm Knapp | Review List | ? | Compare Symbol to BOM is unclear | clarify what you mean by this. Are you comparing the pinots together.
Malcolm Knapp | Review List | ? | Schematic review list is incomplete | Doing one check is not enough. What else do you need to check to confirm things are correct
Malcolm Knapp | Review List | ? | Library review missing | Add Review
Malcolm Knapp | Review List | ? | Layout Review missing | Add Review
Malcolm Knapp | Review List | ? | Cable diagram review missing | Add Review
Malcolm Knapp | Release List | ? | No version | Add a version
Malcolm Knapp | Release List | ? | No change from example | It is unlikely that you will do exactly what I do so you should look through the list and confirm all the steps are accurate. For example do you upload FM to SVN? Make this list your own list.
Malcolm Knapp | Feature Block Diagram | Mark 1 | Overall it is clear and easy to read | :)
Malcolm Knapp | Feature Block Diagram | Mark 1 | Boxes are not the same size which makes it harder to read | Use a standard box size. I make it a group with text in side. If I need a bigger box to fit more lines then I make it bigger but not otherwise
Malcolm Knapp | Feature Block Diagram | Mark 1 | Wire signal is hard to read. | Make the line the same thickness and the power lines
Malcolm Knapp | Feature Block Diagram | Mark 1 | AC and DC portion are hard to distinguish | Use different line styles for the AC and DC signals
Malcolm Knapp | Feature Block Diagram | Mark 1 | Electric Road? | Did you mean Electric Load.
Malcolm Knapp | Feature Block Diagram | Mark 1 | No need for device boundaries around the Battery, Computer and Electric Load | I assume these are off the shelf so you do not need a boundary line around them
Malcolm Knapp | Feature Block Diagram | Mark 1 | 5V comes direct from the battery? | Is that correct? If so why go through the regulator
Malcolm Knapp | Feature Block Diagram | Mark 1 | Nothing distinguishes the input and output signal processing blocks | Give them different names
Malcolm Knapp | Feature Block Diagram | Mark 1 | Is The Electronic Load part of this design? | If it only testing equipment it is not part of the design it should be removed
Malcolm Knapp | Product Definition | Mark 1 | Spell check!! | Spell check!!
Malcolm Knapp | Product Definition | Mark 1 | Over all it is quite clear and pretty complete | :)
Malcolm Knapp | Product Definition | Mark 1 | This information seems redundant - Must be able to take a variable DC voltage intput - Must be able to produce a constant AC voltage output - Must be able to be turned off as the battery is depleted - Must be able to realtime status of the input and output V. | These characteristics show up in the Feature List so they do not need to be repeated in the Product Characteristics
Malcolm Knapp | Product Definition | Mark 1 | Template text still in document. | All text in all CAPS, like "INSERT DEVICE 1 NAME" should be replaced with the specifics on your project
Malcolm Knapp | Product Definition | Mark 1 | Step down transformer is referred to Step Up Transformer in the block diagram | Synchronize names
Malcolm Knapp | Product Definition | Mark 1 | This seems to say the same information and the block diagram. -Reads in voltage at inverter input and output -Reads in frequency at output -Can send voltage data to a wired device for viewing -Can recieve commands from a wired device -Can send an ON or OFF signal to the inverter Also do you mean the Computer when you so "Wire device" | Can this be simplified?
Malcolm Knapp | Product Definition | Mark 1 | No input or output Signal Processor Features | Add them
Malcolm Knapp | Product Definition | Mark 1 | Battery and Computer Feature are missing | Add them
Malcolm Knapp | Product Definition | Mark 1 | These characteristics are captured in the block diagram and in the name of the block -Takes in battery voltage -Constant voltage to power the central processor | Think of characteristics the regulator must have that are not captured other places. For example things like accuracy, max current output, noise rejection.
Malcolm Knapp | Product Definition | Mark 1 | "push power" is unclear | can you clarify what this means in terms of the inverter operation. Does the frequency change? Impedance?
Malcolm Knapp | Product Definition | Mark 1 | Events are missing from Detailed Behavior | I will show you what this means in class
Malcolm Knapp | Product Definition | Mark 1 | The Battery - Inverter and Inverter - Grid interface are missing | add them
Malcolm Knapp | Product Definition | Mark 1 | Command definition are good | :)
Malcolm Knapp | Product Definition | Mark 1 | "warning to device" is unclear | Clarify what this means. Do you mean the computer?
Malcolm Knapp | Product Definition | Mark 1 | "Processor sends warning to device of low voltage every 3s" implies a different state | Add it. Maybe it could be called the Warning state